## HTTP-5310- Capstone_Timesheet
Week_1 | Activities | Date | Time (hrs)
| Kickoff Meeting/Introduction | 2026-01-15 | 1.3
| Meeting with Bernie | 2026-01-15 | 0.15
| Tech Stack choices | 2026-01-15 | 2
| Create Github Repo + ReadMe file | 2026-01-15 | 1.15
| Work on website Theme | 2026-01-16 | 4.75
| Finalize Theme + colors + typography | 2026-01-16 | 3.5
| Requirements Document | 2026-01-16 | 5.75
| Timeline | 2026-01-17 | 5
| Technical Barriers Assessment Doc file | 2026-01-17 | 5.5
| Work on User Stories | 2026-01-19 | 4.75
| Create Basic Wireframes for all the pages | 2026-01-21 | 4.75
| Total |  | 38.6
Week_2 | Activities | Date | Time (hrs)
| Review wireframe feedback | 2026-01-22 | 1.5
| Update wireframes | 2026-01-22 | 2
| Finalize wireframes | 2026-01-22 | 2
| Update feature list | 2026-01-23 | 2
| Organize feature priorities | 2026-01-23 | 2
| Review course critical path | 2026-01-24 | 1.5
| Create project milestones | 2026-01-24 | 2.5
| Finalize project timeline | 2026-01-24 | 2
| Identify technical risks | 2026-01-25 | 1.75
| Identify content risks | 2026-01-25 | 2
| Write mitigation strategies | 2026-01-25 | 2.75
| Define UX goals | 2026-01-26 | 2
| Accessibility research (WCAG/AODA) | 2026-01-26 | 2
| Document accessibility considerations | 2026-01-26 | 1.15
| Documentation cleanup | 2026-01-27 | 2.5
| Start Working on Figma | 2026-01-27 | 3.75
| Total |  | 33.4
Week_3 | Activities | Date | Time (hrs)
| Wireframe in Figma (Hospital Logo Design) | 2026-01-30 | 1.5
| Wireframe in Figma (Hospital NavBar set up) | 2026-01-30 | 1.75
| Wireframe in Figma (Hospital NavBar, Hero Section, specialties) | 2026-01-30 | 2.15
| Wireframe in Figma (Add Doctor section and deatils) | 2026-02-01 | 2.75
| Wireframe in Figma (Home page - created) | 2026-02-02 | 3.75
| Total |  | 11.9
Week_4 | Activities | Date | Time (hrs)
| Wireframe in Figma Lo-fi prototype (Home, Login, Register, Services) | 2026-02-06 | 3.75
| Creat pages find doctors, book appointment, doctor pages | 2026-02-08 | 3.25
| Prototyping pages | 2026-02-08 | 4.5
| Add pages for patient, Doctors | 2026-02-09 | 3.75
| Add pages for Admin | 2026-02-10 | 3.5
| Total |  | 18.75
Week_5 | Activities | Date | Time (hrs)
| Add new pages (Staff view, Contact us) | 2026-02-13 | 2.15
| Wireframe in Figma Prototyping) (Public Pages) | 2026-02-13 | 3.75
| Wire frame Prototyping (All pages) | 2026-02-16 | 3.5
| Revised Requirment document file | 2026-02-16 | 2.5
| Total |  | 11.9
Week_6 | Activities | Date | Time (hrs)
| Figma User Testing (for 2 Users) | 2026-02-20 | 1.75
| Figma User Testing (for 3 Users) | 2026-02-21 | 2
| Mentor Draft Email | 2026-02-22 | 0.25
| Mentor Checklist | 2026-02-23 | 1.75
| set up the Laravel project, connected the database, installed the login/register system, added user roles (patient, doctor, admin), created role-based dashboard routes, and worked on debugging the login/session issue. | 2026-02-23 | 3.75
| Total |  | 9.5
Week_7 | Activities | Date | Time (hrs)
| Worked on homepage UI improvements including navbar hover effects, updated Register button to primary blue, refined hero section layout and styling, adjusted text colors, and improved overall visual clarity. | 2026-02-27 | 3.75
| Completed Home page (Hero section) | 2026-02-28 | 1.75
| Completed Home page (Services section) | 2026-02-28 | 2.15
| Completed Home page (Footer section) | 2026-02-28 | 0.45
| Revised User Testing Report | 2026-03-01 | 2.5
| Add Doctors Pages | 2026-03-02 | 3.75
| Mentor Meeting | 2026-03-04 | 0.75
| Mentor Meeting Thank you email | 2026-03-04 | 0.25
| Mentor meeting Notes for Bernie | 2026-03-04 | 0.5
| Total |  | 14.35
Week_8 | Activities | Date | Time (hrs)
| Create Admin Dashboard UI | 2026-03-06 | 1.75
| Create Admin Appoitment Page UI | 2026-03-06 | 2.5
| Create Admin Profile UI | 2026-03-06 | 2.15
| Create Health Record UI | 2026-03-06 | 2.75
| Create Find-Dotcor Page UI | 2026-03-07 | 2
| Create Services Page UI | 2026-03-07 | 1.75
| Create Book-appointment Form UI | 2026-03-07 | 1.15
| Create Contact US Page UI | 2026-03-07 | 0.75
| Solve Error for find doctor Page + create Doctor Profile pages for 5 Doctors | 2026-03-08 | 3.75
| Services Page UI Connect with Services page and department pages (Controller + model) | 2026-03-08 | 4.15
| Implement Book Appointment Form functionality (Controller + Model + Route) | 2026-03-09 | 2.25
| Create Appointments Database Table and connect form to MySQL | 2026-03-09 | 1.75
| Improve Book Appointment UI and form validation | 2026-03-09 | 1
| Modified some Css & Page in Portfolio | 2026-03-11 | 1.75
| Total |  | 29.45
Week_9 | Activities | Date | Time (hrs)
| Connected patient dashboard with database to display upcoming and recent appointments dynamically. | 2026-03-12 | 2.75
| Create New page for patient (record page) + connect with databse | 2026-03-13 | 1.75
| Create New page for patient (Edit appointment) + connect with databse | 2026-03-13 | 2.75
| Fully Dynamic Patient Pofile ready + Testing | 2026-03-13 | 1.5
| Refactored Laravel controllers and models to improve database handling for appointments, departments, services, and patient modules. | 2026-03-15 | 1.5
| Improved Find Doctor page and connected doctor profiles dynamically with database data. | 2026-03-15 | 2
| Created and connected Services and Department Details pages with backend database records. | 2026-03-15 | 1.75
| Updated Blade layouts for site, admin, and doctor panels to maintain consistent UI and navigation across pages. | 2026-03-15 | 1.25
| Added migrations and models for doctor availability and improved database structure for appointments. | 2026-03-15 | 1.5
| Performed testing and debugging of patient, doctor, and admin pages to ensure correct data display and functionality. | 2026-03-15 | 1
| Fixed duplicate department/service routes and connected department & service detail pages to correct controllers and blade views. | 2026-03-16 | 1.25
| Created Staff View page with appointment status update feature and added Staff user role to the system. | 2026-03-16 | 2
| Auto-complete past appointments logic added to PatientController for dashboard and appointments pages. | 2026-03-16 | 0.75
| Added Book Appointment CTA to patient dashboard and appointments page. | 2026-03-16 | 0.5
| Made Find Doctor, Doctor Profile, Services, and Department pages fully responsive for mobile and tablet. | 2026-03-16 | 1.25
|  | Total | 23.5
Week_10 | Activities | Date | Time (hrs)
| Refactored blade files to clean structure and improve UI consistency | 2026-03-20 | 1.5
| Tested dynamic data rendering for patient and appointment pages. | 2026-03-20 | 1.25
| Performed end-to-end testing of patient workflow from login to appointment booking and confirmation. | 2026-03-20 | 1
| Tested complete doctor flow including profile view and appointment handling. | 2026-03-20 | 1.25
| Validated database integration by checking data consistency across patient, doctor, and appointments modules. | 2026-03-20 | 1
| Tested responsive behavior and cross-device compatibility for all major pages. | 2026-03-20 | 1
| Search Best Hosting option to Deploy Website | 2026-03-20 | 1.5
| Buy Domain (Godaddy) | 2026-03-22 | 1.75
| check Video Tutorial For hosting - how to deploy PHP project + buy hosting from Hosinger | 2026-03-23 | 3.75
| Production Testing (Services, Find a doctor page, services Page, Check Roles ) | 2026-03-23 | 2.15
| Host Website resolve Errors | 2026-03-25 | 1.75
| Update Manage Depatrment Conflicts + update admin panel + final Testing | 2026-03-26 | 3.75
|  | Total | 21.65
Total Hours |  |  | 213