## HTTP-5310- Capstone_Timesheet
Week_1 | Activities | Date | Time (hrs)
| Kickoff Meeting/Introduction | 2026-01-15 | 1.3
| Meeting with Bernie | 2026-01-15 | 0.15
| Tech Stack choices | 2026-01-15 | 2
| Create Github Repo + ReadMe file | 2026-01-15 | 1.15
| Work on website Theme | 2026-01-16 | 4.75
| Finalize Theme + colors + typography | 2026-01-16 | 3.5
| Requirements Document | 2026-01-16 | 5.75
| Timeline | 2026-01-17 | 5
| Technical Barriers Assessment Doc file | 2026-01-17 | 5.5
| Work on User Stories | 2026-01-19 | 4.75
| Create Basic Wireframes for all the pages | 2026-01-21 | 4.75
| Total |  | 38.6
Week_2 | Activities | Date | Time (hrs)
| Review wireframe feedback | 2026-01-22 | 1.5
| Update wireframes | 2026-01-22 | 2
| Finalize wireframes | 2026-01-22 | 2
| Update feature list | 2026-01-23 | 2
| Organize feature priorities | 2026-01-23 | 2
| Review course critical path | 2026-01-24 | 1.5
| Create project milestones | 2026-01-24 | 2.5
| Finalize project timeline | 2026-01-24 | 2
| Identify technical risks | 2026-01-25 | 1.75
| Identify content risks | 2026-01-25 | 2
| Write mitigation strategies | 2026-01-25 | 2.75
| Define UX goals | 2026-01-26 | 2
| Accessibility research (WCAG/AODA) | 2026-01-26 | 2
| Document accessibility considerations | 2026-01-26 | 1.15
| Documentation cleanup | 2026-01-27 | 2.5
| Start Working on Figma | 2026-01-27 | 3.75
| Total |  | 33.4
Week_3 | Activities | Date | Time (hrs)
| Wireframe in Figma (Hospital Logo Design) | 2026-01-30 | 1.5
| Wireframe in Figma (Hospital NavBar set up) | 2026-01-30 | 1.75
| Wireframe in Figma (Hospital NavBar, Hero Section, specialties) | 2026-01-30 | 2.15
| Wireframe in Figma (Add Doctor section and deatils) | 2026-02-01 | 2.75
| Wireframe in Figma (Home page - created) | 2026-02-02 | 3.75
| Total |  | 11.9
Week_4 | Activities | Date | Time (hrs)
| Wireframe in Figma Lo-fi prototype (Home, Login, Register, Services) | 2026-02-06 | 3.75
| Creat pages find doctors, book appointment, doctor pages | 2026-02-08 | 3.25
| Prototyping pages | 2026-02-08 | 4.5
| Add pages for patient, Doctors | 2026-02-09 | 3.75
| Add pages for Admin | 2026-02-10 | 3.5
| Total |  | 18.75
Week_5 | Activities | Date | Time (hrs)
| Add new pages (Staff view, Contact us) | 2026-02-13 | 2.15
| Wireframe in Figma Prototyping) (Public Pages) | 2026-02-13 | 3.75
| Total |  | 5.9